### Project Management Plan: Property Management System Development
#### Overview
This plan outlines the stages and technologies involved in building a comprehensive property management system that supports property management, financial tracking, and personal expenditure management. The focus is on using robust technologies from the start to ensure long-term sustainability and cross-platform compatibility.

### Stage 1: Initial Setup and Core Technologies
Objective: Set up the development environment and establish the core architecture.
Tasks:
1. Development Environment Setup (2 days)
  1. Install Node.js, MySQL, Git, Docker.
  2. Set up an IDE (e.g., Visual Studio Code).
2. Version Control Configuration (1 day)
  1. Initialize Git repository.
  2. Configure Git for source code management and set up branching strategy.
3. Backend Framework Selection (3 days)
  1. Set up Node.js with Express.
  2. Create initial project structure.
4. Database Setup (3 days)
  1. Install and configure MySQL.
  2. Create initial database schemas.
5. Frontend Framework Setup (2 days)
  1. Choose a frontend stack (HTML, CSS, JavaScript).
  2. Set up a basic project using Bootstrap for responsive design.
Technologies:
- Frontend: HTML, CSS, JavaScript, Bootstrap
- Backend: Node.js with Express
- Database: MySQL
- Version Control: Git
- Deployment: Docker for containerization
Timeline: 11 days

### Stage 2: Basic Property Management Features
Objective: Develop basic interfaces and backend functionality for property management.
Tasks:
1. Frontend Development (7 days)
  1. Create property listing page.
  2. Develop Add/Edit property form.
2. Backend API Development (7 days)
  1. Implement RESTful APIs for property management (CRUD operations).
  2. Connect frontend to backend.
3. Database Enhancements (5 days)
  1. Define schemas for properties, stages, and documents.
  2. Implement initial data handling for property management.
4. Document Management Integration (4 days)
  1. Set up file upload/download functionality.
Technologies:
- Frontend: Bootstrap, jQuery
- Backend: Node.js with Express, RESTful APIs
- Database: MySQL
Timeline: 23 days

### Stage 3: Financial Management Implementation
Objective: Implement comprehensive financial tracking for properties, rentals, and rehabilitation projects.
Tasks:
1. Frontend Enhancements (5 days)
  1. Integrate data visualization libraries (e.g., Chart.js).
2. Backend Financial APIs (7 days)
  1. Expand API endpoints for financial data (loans, payments, expenses).
3. Database Expansion (5 days)
  1. Create tables for financial data (loans, payments, expenses, budgets).
4. Feature Development (7 days)
  1. Develop loan and payment tracking system.
  2. Implement expense reporting and categorization.
  3. Set up budget tracking for property rehabilitation.
Technologies:
- Frontend: Chart.js, Bootstrap
- Backend: Node.js with Express
- Database: MySQL
Timeline: 24 days

### Stage 4: Rental and Tenant Management
Objective: Create functionalities for managing rentals and tenants.
Tasks:
1. Frontend Development (5 days)
  1. Design tenant management dashboard.
  2. Create forms for tenant and lease management.
2. Backend Enhancements (7 days)
  1. Secure API endpoints for tenant data transactions.
  2. Implement rental income and expenditure tracking.
3. Database Configuration (5 days)
  1. Create tables for rental income, tenant details, and lease agreements.
Technologies:
- Frontend: Bootstrap, jQuery
- Backend: Node.js with Express
- Database: MySQL
Timeline: 17 days

### Stage 5: Reporting and Tax Preparation
Objective: Develop reporting tools and export functionalities for tax preparation and management overview.
Tasks:
1. Frontend Tools Integration (4 days)
  1. Implement libraries for generating reports (e.g., jsPDF, PapaParse).
2. Backend Query Development (6 days)
  1. Develop complex queries for generating financial reports.
3. Feature Development (7 days)
  1. Create customizable financial reports.
  2. Develop export tools for financial data.
4. Accounting Software Integration (Optional) (5 days)
  1. Investigate integration with accounting software.
Technologies:
- Frontend: jsPDF, PapaParse
- Backend: Node.js with Express
- Database: MySQL
Timeline: 22 days

### Stage 6: Personal Expenditure Tracking and Final Integration
Objective: Finalize the system with personal expenditure tracking and ensure all components are integrated smoothly.
Tasks:
1. Personal Finance UI Development (5 days)
  1. Create UI components for personal financial management.
2. Backend APIs for Personal Data (5 days)
  1. Implement private APIs for secure personal data handling.
3. System Integration and Testing (10 days)
  1. Integrate all system components.
  2. Comprehensive testing and debugging.
4. User Feedback and Adjustments (5 days)
  1. Collect user feedback.
  2. Make necessary adjustments and improvements.
Technologies:
- Frontend: Custom UI components
- Backend: Node.js with Express
- Database: MySQL
Timeline: 25 days

### Stage 7: Deployment and Maintenance
Objective: Deploy the application to a cloud server and enter the maintenance phase.
Tasks:
1. Cloud Deployment Setup (5 days)
  1. Set up cloud infrastructure (AWS or DigitalOcean).
  2. Configure Docker for deployment.
2. Deployment and CI/CD Pipelines (7 days)
  1. Finalize deployment scripts.
  2. Implement CI/CD pipelines for continuous updates.
3. Ongoing Maintenance and Support (Ongoing)
  1. Perform regular updates and patches.
  2. Gather and incorporate user feedback for future enhancements.
Technologies:
Deployment: Docker, AWS/DigitalOcean, CI/CD
Timeline: 12 days + ongoing maintenance

### Overall Timeline and Milestones
- Total Development Time: Approximately 134 days (~4.5 months) for a solo developer.
- Milestones:
  - End of Stage 1: Basic environment setup and architecture (11 days)
  - End of Stage 2: Basic property management features (34 days)
  - End of Stage 3: Financial management implementation (58 days)
  - End of Stage 4: Rental and tenant management (75 days)
  - End of Stage 5: Reporting tools and tax preparation (97 days)
  - End of Stage 6: Personal expenditure tracking and integration (122 days)
  - End of Stage 7: Deployment and maintenance (134 days + ongoing)

### Technology Considerations
- Cross-Platform Compatibility: Ensure responsive design and test thoroughly on Android, iOS, and PC.
- Database Migration: Be prepared for potential migration from MySQL to PostgreSQL if scalability becomes a concern.
- Security: Implement robust security practices, especially for handling financial and personal data.
- Future Scalability: Plan for potential integration with additional services or expansion of features.
This plan should guide you through the development of a robust and scalable property management system that meets your business needs and ensures long-term success.